## Product Backlog
Product Backlog
ID | Story | Estimation | Priority
1 | Reader sign up(Librarian add reader) | 1 | 1
2 | Reader log in and log out | 1 | 3
3 | Reader can view and modify personal information | 2 | 2
4 | Reader can modify password | 1 | 2
5 | Reader can query book by book name or ISBN | 2 | 10
6 | Reader can borrow the book (under librarian's operation) | 3 | 9
7 | Reader can return back the book (under librarian's operation) | 3 | 9
8 | Librarian and Reader can view borrow and return log | 2 | 6
9 | Readers can reserve book | 3 | 5
10 | Reader can view fine | 2 | 4
11 | Librarian log in and log out | 1 | 3
12 | Librarian can modify password | 1 | 2
13 | Librarian can view, edit, add and delete book | 5 | 9
14 | Librarian can view, edit, add and delete reader | 5 | 9
15 | Librarin can calculate reader's fine | 3 | 8
16 | Librarian can add a kind of book with some duplicates (different books have same ISBN but have different book ID) | 3 | 6
17 | Reader can only borrow two books at the same time | 2 | 8
18 | Reader can renew book | 2 | 6

## Sprint Backlog
Sprint Backlog
Sprint One | Id | Name | Estimate(Ideal Days) | Importance
| 1 | Reader sign up(Librarian add reader) | 1 | 1
| 2 | Reader log in and log out | 1 | 3
| 11 | Librarian log in and log out | 1 | 3
| 3 | Reader can view and modify personal information | 2 | 2
| 4 | Reader can modify password | 1 | 2
| 12 | Librarian can modify password | 1 | 2
Sprint Two | 13 | Librarian can view, edit, add and delete book | 5 | 9
| 14 | Librarian can view, edit, add and delete reader | 5 | 9
| 5 | Reader can query book by book name or ISBN | 2 | 10
Sprint Three | 6 | Reader can borrow the book (under librarian's operation) | 3 | 9
| 7 | Reader can return back the book (under librarian's operation) | 3 | 9
| 8 | Librarian and Reader can view borrow and return log | 2 | 6
Sprint Four | 9 | Readers can reserve book | 3 | 5
| 10 | Reader can view fine | 2 | 4
| 15 | Librarin can calculate reader's fine | 3 | 8
| 18 | Reader can renew book | 2 | 6
Sprint Five | 16 | Librarian can add a kind of book with some duplicates (different books have same ISBN but have different book ID) | 3 | 6
| 17 | Reader can only borrow two books at the same time | 2 | 8

## Release Backlog
Release Backlog
| Id | Name | Estimate(Ideal Days) | Importance
Release One（Sprint One） | 1 | Reader sign up(Librarian add reader) | 1 | 1
| 2 | Reader log in and log out | 1 | 3
| 11 | Librarian log in and log out | 1 | 3
| 3 | Reader can view and modify personal information | 2 | 2
| 4 | Reader can modify password | 1 | 2
| 12 | Librarian can modify password | 1 | 2
Release Two(Sprint Three+Sprint Two） | 13 | Librarian can view, edit, add and delete book | 5 | 9
| 14 | Librarian can view, edit, add and delete reader | 5 | 9
| 5 | Reader can query book by book name or ISBN | 2 | 10
| 6 | Reader can borrow the book (under librarian's operation) | 3 | 9
| 7 | Reader can return back the book (under librarian's operation) | 3 | 9
| 8 | Librarian and Reader can view borrow and return log | 2 | 6
Release Three（Sprint Four+Sprint Five） | 9 | Readers can reserve book | 3 | 5
| 10 | Reader can view fine | 2 | 4
| 15 | Librarin can calculate reader's fine | 3 | 8
| 16 | Librarian can add a kind of book with some duplicates (different books have same ISBN but have different book ID) | 3 | 6
| 17 | Reader can only borrow two books at the same time | 2 | 8
| 18 | Reader can renew book | 2 | 6